## Sheet1
Project Estimate
SCOPE OF THE WORK
S.No | Module | Features | Time/Hours | Comments
1 | Interface | Tree view | 40
|  | Permissions as per the access level with file details | 16
2 | File Uploads | Uploading the file with drag and drop box and file input | 24
3 | Search | Minimum and full text search | 40
4 | Access Control | File permissions | 16
5 | Modify File Details | With Modal box | 8
6 | Testing and delivering |  | 16
|  | Total | 160